## Tasks
Task | Start Date | End Date | Progress | Team | Involved Stakeholders | StartDate | TaskHeight
HR Dashboard Revamp | 2025-01-01 | 2025-12-01 | In Progress | Systems | BI Team, HR Tech, People Operations, Internal Audit | 2025-01-01 | 21
Talent Acquisition System Migration | 2025-01-01 | 2025-12-01 | Not Started | Systems | Recruitment Team, HR Tech, IT Services, Group Finance, Compliance | 2025-01-27 | 11
Centralized Leave Management System | 2025-01-01 | 2025-11-01 | In Progress | Systems | HR Ops, People Partners, Legal | 2025-02-22 | 34
Cloud Migration of HR Files and Records | 2025-01-01 | 2025-12-01 | Completed | Systems | HR Tech, Records Management, IT Infra, Security & Compliance | 2025-03-20 | 27
Integration of HR Chatbot Across All Units | 2025-01-01 | 2025-12-01 | In Progress | Systems | AI Team, HR Tech, Group IT, Learning & Development, Legal | 2025-04-15 | 19
Succession Planning Workflow Automation | 2025-01-01 | 2025-12-01 | Not Started | Systems | People Analytics, Leadership Team | 2025-11-05 | 22
Legacy System Data Archival | 2025-01-01 | 2025-09-01 | In Progress | Systems | IT Infra, HRSS, Data Governance Committee, Archives Unit | 2025-02-07 | 45
Deploy Gen AI Assistant for Employee Services | 2025-01-01 | 2025-06-01 | Not Started | Systems | AI Lab, HR Tech, External Consultants | 2025-07-28 | 35
Diversity & Inclusion Dashboard Deployment | 2025-01-01 | 2025-06-01 | In Progress | Systems | DEI Council, HRBP Team | 2025-08-23 | 22
Develop Machine Learning Models for Attrition Risk Prediction | 2025-07-01 | 2025-09-01 | Not Started | Data | Data Science Team, Workforce Analytics | 2025-09-18 | 21
Real-time KPI Monitoring System for HR Decision-Makers | 2025-04-01 | 2025-06-01 | Completed | Data | Business Intelligence, HR Leadership | 2025-09-11 | 44
Launch Mobile App for TM Feedback Analysis and Visualization | 2025-04-01 | 2025-06-01 | In Progress | Data | UX Team, TM Strategy, HR Tech, People Analytics, Mobile Dev Team | 2025-12-31 | 18

## TeamMembers
ID | Name | Team | Grade
1 | Ayan | Systems | Lead - HR Information Systems
2 | Maleesha | Systems | Trainee - HR Tech and Systems
3 | Ramesh | Systems | Deputy Manager - HR Digital Strategy
4 | Janani | Systems | Specialist - HR Operations
5 | Nadeesha | Systems | Senior Analyst - HR Systems
6 | Tharanga | Systems | Head - HR Systems
7 | Chamod | Systems | Consultant - HR System Implementation
8 | Bimali | Systems | Officer - HR Systems
9 | Thisura | Systems | Analyst - HR Data and Reporting
10 | Hiruni | Systems | Trainee - HR Analytics
11 | Dhanuka | Data | Lead Analyst - Talent Insights
12 | Rehan | Data | Analyst - Workforce Analytics
13 | Hiranya | Data | Specialist - Talent Data Management
14 | Udani | Data | Intern - Workforce Intelligence

## ProfilePictures
ID | Name | URL
1 | Ayan | C:\Personal\webwoods\goals\images\Ayan.png
2 | Maleesha | C:\Personal\webwoods\goals\images\Maleesha.png
3 | Ramesh | C:\Personal\webwoods\goals\images\Ramesh.png
4 | Janani | C:\Personal\webwoods\goals\images\Janani.png
5 | Nadeesha | C:\Personal\webwoods\goals\images\Nadeesha.png
6 | Tharanga | C:\Personal\webwoods\goals\images\Tharanga.png
7 | Chamod | C:\Personal\webwoods\goals\images\Chamod.png
8 | Bimali | C:\Personal\webwoods\goals\images\Bimali.png
9 | Thisura | C:\Personal\webwoods\goals\images\Thisura.png
10 | Hiruni | C:\Personal\webwoods\goals\images\Hiruni.png
11 | Dhanuka | C:\Personal\webwoods\goals\images\Dhanuka.png
12 | Rehan | C:\Personal\webwoods\goals\images\Rehan.png
13 | Hiranya | C:\Personal\webwoods\goals\images\Hiranya.png
14 | Udani | C:\Personal\webwoods\goals\images\Udani.png

## Task_TeamMembers
Task | Assignees | Grade | Rank
Talent Acquisition System Migration | Ayan | Lead - HR Information Systems | 1
Centralized Leave Management System | Ramesh | Deputy Manager - HR Digital Strategy | 1
Centralized Leave Management System | Udani | Intern - Workforce Intelligence | 2
Cloud Migration of HR Files and Records | Janani | Specialist - HR Operations | 1
Cloud Migration of HR Files and Records | Chamod | Consultant - HR System Implementation | 1
Integration of HR Chatbot Across All Units | Nadeesha | Senior Analyst - HR Systems | 1
Succession Planning Workflow Automation I | Ayan | Lead - HR Information Systems | 1
Succession Planning Workflow Automation I | Hiranya | Specialist - Talent Data Management | 2
Succession Planning Workflow Automation II | Janani | Specialist - HR Operations | 1
Succession Planning Workflow Automation II | Hiranya | Specialist - Talent Data Management | 2
Integration of HR Chatbot Across All Units | Janani | Specialist - HR Operations | 1
Succession Planning Workflow Automation | Thisura | Analyst - HR Data and Reporting | 1
Succession Planning Workflow Automation | Hiruni | Trainee - HR Analytics | 2
Legacy System Data Archival | Hiranya | Specialist - Talent Data Management | 1
Legacy System Data Archival | Ayan | Lead - HR Information Systems | 2
Deploy Gen AI Assistant for Employee Services | Bimali | Officer - HR Systems | 1
Deploy Gen AI Assistant for Employee Services | Tharanga | Head - HR Systems | 2
Launch Mobile App for TM Feedback Analysis and Visualization | Tharanga | Head - HR Systems | 1
Launch Mobile App for TM Feedback Analysis and Visualization | Maleesha | Trainee - HR Tech and Systems | 2
Diversity & Inclusion Dashboard Deployment | Bimali | Officer - HR Systems | 1
Develop Machine Learning Models for Attrition Risk Prediction | Maleesha | Trainee - HR Tech and Systems | 2
Develop Machine Learning Models for Attrition Risk Prediction | Ayan | Lead - HR Information Systems | 1
Real-time KPI Monitoring System for HR Decision-Makers | Tharanga | Head - HR Systems | 2
Streamline TM Recruitment with New App for Strategic Insights. | Dhanuka | Lead Analyst - Talent Insights | 1

## Dates
Date
2025-01-01
2025-01-02
2025-01-03
2025-01-04
2025-01-05
2025-01-06
2025-01-07
2025-01-08
2025-01-09
2025-01-10
2025-01-11
2025-01-12
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09
2025-04-10
2025-04-11
2025-04-12
2025-04-13
2025-04-14
2025-04-15
2025-04-16
2025-04-17
2025-04-18
2025-04-19
2025-04-20
2025-04-21
2025-04-22
2025-04-23
2025-04-24
2025-04-25
2025-04-26
2025-04-27
2025-04-28
2025-04-29
2025-04-30
2025-05-01
2025-05-02
2025-05-03
2025-05-04
2025-05-05
2025-05-06
2025-05-07
2025-05-08
2025-05-09
2025-05-10
2025-05-11
2025-05-12
2025-05-13
2025-05-14
2025-05-15
2025-05-16
2025-05-17
2025-05-18
2025-05-19
2025-05-20
2025-05-21
2025-05-22
2025-05-23
2025-05-24
2025-05-25
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30
2025-05-31
2025-06-01
2025-06-02
2025-06-03
2025-06-04
2025-06-05
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2025-06-10
2025-06-11
2025-06-12
2025-06-13
2025-06-14
2025-06-15
2025-06-16
2025-06-17
2025-06-18
2025-06-19
2025-06-20
2025-06-21
2025-06-22
2025-06-23
2025-06-24
2025-06-25
2025-06-26
2025-06-27
2025-06-28
2025-06-29
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31

## Task_SubTask
Task | Sub Task | Start date | End date | Status | Assignee's Comment | Director's Comment | Number
HR Dashboard Revamp | Wireframe Design for Dashboard UI | 2025-01-01 | 2025-02-28 | In Progress | All good, on track! | Keep up the good work! | 1
HR Dashboard Revamp | Integrate Data Sources | 2025-03-01 | 2025-05-31 | Not Started | Minor hiccups, but manageable | Follow up this! | 1
HR Dashboard Revamp | KPI Definition and Calculation | 2025-06-01 | 2025-08-31 | In Progress | Slight delay, catching up soon | Project update needed | 1
HR Dashboard Revamp | User Access Setup | 2025-09-01 | 2025-12-31 | Completed |  | Excellent work! | 1
Talent Acquisition System Migration | Requirements Gathering from Recruitment Team | 2025-01-01 | 2025-03-31 | In Progress |  | Well done | 1
Talent Acquisition System Migration | Data Migration from Legacy System | 2025-04-01 | 2025-06-30 | Not Started | Resource issues, but under control. | Keep up the good work! | 1
Talent Acquisition System Migration | Vendor API Integration | 2025-07-01 | 2025-12-31 | Not Started | All good, on track! |  | 1
Talent Acquisition System Migration | System Testing and QA | 2025-01-01 | 2025-02-28 | In Progress | Minor hiccups, but manageable | Project update needed | 1
Centralized Leave Management System | Policy Mapping Across Units | 2025-03-01 | 2025-05-31 | Not Started | Slight delay, catching up soon | Excellent work! | 1
Centralized Leave Management System | Leave Approval Workflow Setup | 2025-06-01 | 2025-08-31 | In Progress |  | Well done | 1
Centralized Leave Management System | Mobile App Leave Request Integration | 2025-09-01 | 2025-11-30 | Not Started |  | Keep up the good work! | 1
Cloud Migration of HR Files and Records | Inventory of Existing Records | 2025-01-01 | 2025-04-30 | Not Started | Resource issues, but under control. |  | 1
Cloud Migration of HR Files and Records | Secure Cloud Storage Setup | 2025-05-01 | 2025-08-31 | Completed | All good, on track! | Follow up this! | 1
Cloud Migration of HR Files and Records | Role-based Access Control | 2025-09-01 | 2025-12-31 | Completed | Minor hiccups, but manageable | Project update needed | 1
Integration of HR Chatbot Across All Units | Use Case Collection from Departments | 2025-01-01 | 2025-04-30 | In Progress | Slight delay, catching up soon | Excellent work! | 1
Integration of HR Chatbot Across All Units | Language Model Integration | 2025-05-01 | 2025-08-31 | In Progress |  | Well done | 1
Integration of HR Chatbot Across All Units | Internal Testing & Feedback Collection | 2025-09-01 | 2025-12-31 | Not Started |  | Keep up the good work! | 1
Succession Planning Workflow Automation | Define Critical Roles and Successors | 2025-01-01 | 2025-03-01 | In Progress | Resource issues, but under control. | Follow up this! | 1
Succession Planning Workflow Automation | Automate Workflow Triggers | 2025-03-01 | 2025-06-01 | Completed | All good, on track! | Project update needed | 1
Succession Planning Workflow Automation | Dashboard for Succession Pipeline | 2025-06-01 | 2025-07-01 | In Progress | Minor hiccups, but manageable | Excellent work! | 1
Legacy System Data Archival | Identify Archival Criteria | 2025-07-01 | 2025-07-30 | Not Started | Slight delay, catching up soon | Well done | 1
Legacy System Data Archival | Migrate Approved Data | 2025-07-22 | 2025-09-27 | Not Started |  | Keep up the good work! | 1
Legacy System Data Archival | Retire Obsolete Systems | 2025-09-23 | 2025-11-27 | In Progress |  |  | 1
Legacy System Data Archival | Compliance Review and Approval | 2025-01-01 | 2025-02-28 | Not Started | Resource issues, but under control. | Follow up this! | 1
Deploy Gen AI Assistant for Employee Services | Define User Queries for Gen AI Assistant | 2025-03-01 | 2025-05-31 | Completed | All good, on track! | Project update needed | 1
Deploy Gen AI Assistant for Employee Services | Train Model with Internal HR Data | 2025-06-01 | 2025-07-31 | In Progress | Minor hiccups, but manageable | Excellent work! | 1
Deploy Gen AI Assistant for Employee Services | Deploy on Employee Self-Service Portal | 2025-08-01 | 2025-09-30 | Not Started | Slight delay, catching up soon | Well done | 1
Diversity & Inclusion Dashboard Deployment | Collect DEI Metrics from Business Units | 2025-01-01 | 2025-04-30 | Completed |  | Keep up the good work! | 1
Diversity & Inclusion Dashboard Deployment | Visualize Gender and Ethnicity Trends | 2025-05-01 | 2025-06-30 | In Progress |  | Follow up this! | 1
Diversity & Inclusion Dashboard Deployment | Enable Drill-through by Region/Department | 2025-07-01 | 2025-12-01 | Not Started | Resource issues, but under control. | Project update needed | 1
Develop Machine Learning Models for Attrition Risk Prediction | Prepare Historical Attrition Dataset | 2025-01-01 | 2025-02-28 | Not Started | All good, on track! | Excellent work! | 1
Develop Machine Learning Models for Attrition Risk Prediction | Train Decision Tree and Random Forest Models | 2025-03-01 | 2025-04-30 | Not Started | Minor hiccups, but manageable | Well done | 1
Develop Machine Learning Models for Attrition Risk Prediction | Deploy Model into Analytics Environment | 2025-05-01 | 2025-05-31 | Completed | All good, on track! | Keep up the good work! | 1
Real-time KPI Monitoring System for HR Decision-Makers | Define Real-Time KPIs with Stakeholders | 2025-06-01 | 2025-06-30 | Completed | Minor hiccups, but manageable | Follow up this! | 1
Real-time KPI Monitoring System for HR Decision-Makers | Create Alert Triggers and Notification Logic | 2025-07-01 | 2025-07-31 | Completed | Slight delay, catching up soon | Project update needed | 1
Real-time KPI Monitoring System for HR Decision-Makers | Visualize KPIs in Executive Dashboard | 2025-08-01 | 2025-08-31 | In Progress |  | Excellent work! | 1
Launch Mobile App for TM Feedback Analysis and Visualization | Design App Wireframes and UX | 2025-09-01 | 2025-09-30 | Not Started |  | Well done | 1
Launch Mobile App for TM Feedback Analysis and Visualization | Set Up Feedback Collection Engine | 2025-04-01 | 2025-04-30 | Not Started | Resource issues, but under control. | Keep up the good work! | 1
Launch Mobile App for TM Feedback Analysis and Visualization | Integrate with HR Data Pipeline | 2025-05-01 | 2025-05-31 | In Progress | All good, on track! |  | 1
Launch Mobile App for TM Feedback Analysis and Visualization | Generate Automated Visual Reports | 2025-06-01 | 2025-06-30 | Completed | Minor hiccups, but manageable | Project update needed | 1

## UsualTasks
Task | Start Date | End Date | Progress
Automate Monthly Payroll Calculation & Reporting | 2025-01-01 | 2025-12-01 | In Progress
Implement Continuous Testing Framework for HR Systems | 2025-01-01 | 2025-01-01 | In Progress
Establish HR Master Data Governance Framework | 2025-10-01 | 2025-12-01 | In Progress
Launch Interactive HR Systems Learning Hub | 2025-03-01 | 2025-03-31 | In Progress
Host Quarterly Digital HR Roundtable | 2025-10-01 | 2025-10-31 | In Progress
Regional Rollout of Unified Talent Management Platform | 2025-01-01 | 2025-12-01 | In Progress
Develop & Execute HR Tech Innovation Roadmap | 2025-01-01 | 2025-12-01 | In Progress
Align Talent Cycle Tools with Annual Business Strategy | 2025-01-01 | 2025-12-01 | In Progress
Standardize HR System Change Request Process Across BUs | 2025-01-01 | 2025-12-01 | In Progress
Design User Experience Enhancements Based on Feedback Analytics | 2025-01-01 | 2025-12-01 | In Progress
Define ERP Transformation Blueprint for Future Scalability | 2025-01-01 | 2025-01-06 | In Progress
Evaluate Next-Gen HCM Platform Hosting & Integration Strategies | 2025-01-01 | 2025-01-06 | In Progress